## UAT Overview
REV-71 · ALM Invoice Consolidation Code
User Acceptance Testing (UAT) Pack
Environment | FULLUAT (full-copy UAT sandbox)
Login URL | https://lawbusinessresearch--fulluat.sandbox.lightning.force.com
Field to check | ALM Total Contract Value (on each product line)
Prepared | 18 Jun 2026
Owner / approver | Cayla Vichot — ALM Sales Ops
What we are testing
When a deal has more than one product, the system should automatically put a 1, 2 or 3 in the ALM Total Contract Value field on every line, so Integra rolls the deal onto one invoice line. This pack checks it picks the right code on every type of deal — and, just as importantly, that it leaves the field blank when it should.
How to run each test
1. Open the 'Test Cases' tab and pick a row.
2. Build / edit the deal exactly as the 'How to set it up' column says.
3. Save, then look at the ALM Total Contract Value field on the product lines.
4. Compare it to 'Expected result'. Put what you actually saw in 'Actual result'.
5. Set 'Status' to Pass or Fail (dropdown). Add your name, the date, and any notes.
Live progress
Total tests
Passed
Failed
Blocked
Not run yet
Sign-off
UAT completed by
Outcome (Approved / Rejected)
Date
Comments

## Test Cases
ID | Group | Scenario (what you're testing) | How to set it up | Expected result | Actual result | Status | Tester | Date | Comments
A1 | A — Core codes | Law.com worth more than International | Create a deal with Law.com + Law.com International. Price Law.com higher. | Code 1 on every product line
A2 | A — Core codes | International worth more than Law.com | Same two products; price Law.com International higher. | Code 3 on every line
A3 | A — Core codes | Equal value (the tie) | Same two products, priced exactly equal. | Code 1 (Premium wins the tie — confirmed by Brady)
A4 | A — Core codes | Global Leaders is on the deal | Add Global Leaders (GLBM) alongside any other product. | Code 2 on every line (Global Leaders always wins)
A5 | A — Core codes | Law.com + a small add-on (no International) | Law.com plus a smaller add-on (e.g. NV). No International. | Code 1
A6 | A — Core codes | International + a small add-on (no Law.com) | Law.com International plus a smaller add-on. No Law.com. | Code 3
B1 | B — Correctly blank | A single product on its own | A deal with only ONE product (e.g. just Law.com International). | Blank — no code. CONFIRMED correct: one line has nothing to consolidate.
B2 | B — Correctly blank | A single bundle on its own | One bundle product, nothing else. | Blank — no code
B3 | B — Correctly blank | Several products, none a core brand | Two products that are NOT Law.com, International or Global Leaders. | Blank — and a 'no anchor' note is logged for review
C1 | C — Keeps up live | Add a second product | Start from a single-product deal (blank), then add a second qualifying product. | Code now appears on the lines
C2 | C — Keeps up live | Remove down to one product | Take a coded multi-product deal and delete lines until one remains. | Code clears back to blank
C3 | C — Keeps up live | Re-price so the bigger brand flips | On a Law.com + International deal, change pricing so the other brand becomes larger. | Code flips automatically (1 to 3, or 3 to 1)
D1 | D — Every sales path | Built through a Quote (CPQ) | Build the deal on a Quote, add lines, save / calculate. | Code appears on the quote AND carries down to the opportunity
D2 | D — Every sales path | Products added straight to the Opportunity | Add products directly on an Opportunity (no quote). | Code appears
D3 | D — Every sales path | Renewal deal | A renewal-type deal with qualifying products. | Code applied per the rules
D4 | D — Every sales path | Amendment deal | An amendment-type deal with qualifying products. | Code applied per the rules
E1 | E — Volume & safety | Large deal / many lines | A deal with many product lines (and/or several quotes). | Every line carries the same, correct code
E2 | E — Volume & safety | Bundle with components | A bundle that has child / component lines under a main product. | Only the main lines are coded; child components stay blank
E3 | E — Volume & safety | Re-save with no changes | Open a correctly-coded deal and save again without changing anything. | Nothing changes — no re-stamp, no flicker
E4 | E — Volume & safety | (Admin, optional) Emergency off-switch | Admin turns the kill switch on, then edits a deal. | No codes are added or changed while the switch is on

## Rules Reference
The coding rules in plain English
If the deal contains… | Code | Why
Global Leaders (GLBM) — anywhere on the deal | 2 | Global Leaders is always the primary product
Law.com + International, Law.com worth more | 1 | Law.com Premium bundle
Law.com + International, International worth more | 3 | Law.com International bundle
Law.com + International, worth exactly the same | 1 | Premium wins the tie (confirmed by Brady, 15 Jun 2026)
Law.com only (with or without add-ons, 2+ lines) | 1 | Law.com is the anchor
International only (with or without add-ons, 2+ lines) | 3 | International is the anchor
Several products but none is a core brand | (blank) | No anchor — left blank and logged for review
A single product on its own | (blank) | Nothing to consolidate (confirmed correct, 18 Jun 2026)
Note: Law.com Pro and Mid-Market are not given a Total Contract Value code — they use different codes, and the system leaves them alone.