# Account Attorney-Count Field Consolidation — Phase 2: Remediation & Rollback Plan

Date: 2026-06-19 Status: PLAN ONLY — no org writes. Execution is Phase 3, gated step-by-step by explicit approval. Companion: see Phase 1 audit for evidence behind every reference below.

- SURVIVOR (keep): Account.Number_of_Attorneys__c — Number(18,0), Id 00NTm000002XohdMAC

- RETIRE (remove): Account.of_Attorneys__c — Number(18,0), Id 00NPx00000ACARFMA5

- Do not touch: Account.Total_US_Attorneys__c, Account.Total_Non_US_Attorneys__c

## Conflict tie-break (the one business decision baked into this plan)

Default = RETIRE wins. Where both fields are populated but differ (622 records), Number_of_Attorneys__c is overwritten with of_Attorneys__c. Rationale: the retire field is the ALM-maintained source, and this keeps the formula repoint (Step 4) behavior-neutral because Industry_Category__c / ALM_Industry_Category_Code__c read the retire value *today*. Requires ALM data-team sign-off (it changes 622 survivor values). If they prefer SURVIVOR-wins, Step 3 shrinks to the 109 blanks only and Step 4 becomes behavior-*changing* for 622 accounts — call that out to stakeholders.

# Guiding principles

- Nothing destructive without explicit, separate confirmation. Field deletion (Step 8) is isolated from everything else.

- Sandbox → Full UAT → Production. Build/validate metadata in KJDEV; rehearse the data migration in FULLUAT (prod-like data) before PROD.

- Behavior-neutral ordering in PROD: migrate data before repointing formulas, so the formulas' output doesn't change when they flip to the survivor.

- Back up before every change — metadata via git baseline; data via a pre-migration CSV export (which doubles as the rollback source).

- Re-prove zero references (Phase 1 audit re-run) before any deprecation/deletion.

# Environment & sequencing overview

| # | Step | Type | KJDEV | FULLUAT | PROD | Reversible? |
| --- | --- | --- | --- | --- | --- | --- |
| 0 | Branch + baseline retrieve | git/metadata | ✅ | — | — | n/a |
| 1 | FLS parity for survivor | metadata | ✅ | ✅ | ✅ | yes (redeploy) |
| 2 | Pre-migration data backup (export) | data | — | ✅ | ✅ | n/a (is the backup) |
| 3 | Data migration: survivor ⃪ retire | data | n/a (0 records) | ✅ | ✅ | yes (reload backup) |
| 4 | Repoint 2 formula fields → survivor | metadata | ✅ | ✅ | ✅ | yes (redeploy) |
| 5 | Swap field on 2 layouts | metadata | ✅ | ✅ | ✅ | yes (redeploy) |
| 6 | Re-run Phase 1 audit (prove 0 refs) | verify | ✅ | ✅ | ✅ | n/a |
| 7 | Redirect stewardship + Data Cloud stream | config/people | — | — | ✅ | yes |
| 8 | Deprecate of_Attorneys__c | metadata | ✅ | ✅ | ✅ | yes (redeploy) |
| 9 | DELETE of_Attorneys__c (separate sign-off) | destructive | ✅ | ✅ | ✅ | 15-day undelete window |

Critical PROD ordering: Step 1 → Step 2 → Step 3 (data) must finish before Step 4 (formula deploy) → Step 5 → Step 6 → Step 7 → soak → Step 8 → soak → Step 9. In KJDEV there's no data, so Steps 2/3 are skipped; we instead create a few synthetic test Accounts (see Step 4 validation) to prove the repoint is output-neutral.

# Step 0 — Branch + baseline retrieve (KJDEV)

Action. New git branch; retrieve the exact components we will touch so we have a pristine pre-edit baseline to diff against and to redeploy for rollback.

git switch -c attorney-field-consolidation

# clear dead proxy vars first (per session)

sf project retrieve start --target-org KJDEV \

-m "CustomField:Account.of_Attorneys__c" \

-m "CustomField:Account.Number_of_Attorneys__c" \

-m "CustomField:Account.Industry_Category__c" \

-m "CustomField:Account.ALM_Industry_Category_Code__c" \

-m "Layout:Account-Firm Layout" \

-m "Layout:Account-Office Layout - Data Team" \

-m "PermissionSet:ALM fields - Data team" \

-m "PermissionSet:Additional Account Permission for ALM CS team"

git add -A && git commit -m "Baseline: attorney-field consolidation (pre-edit)"

Rollback. git revert/redeploy this baseline commit restores any metadata component.

# Step 1 — FLS parity for the survivor (metadata)

Why. After cutover, anyone who could read/edit of_Attorneys__c must retain that on Number_of_Attorneys__c. Phase 1 found the survivor lacks parity in two permission sets. (Profiles already had parity in the sandbox; regenerate the exact delta from the PROD `FieldPermissions` snapshot before deploying — see query below — because prod may differ.)

Gap to close (from Phase 1, confirm in prod):

| Permission set | retire | survivor today | change |
| --- | --- | --- | --- |
| ALM fields - Data team | R/W | R only | add Edit to survivor |
| Additional Account Permission for ALM CS team | R/W | absent | add survivor R/W |

Generate the authoritative delta (read-only):

-- run against the target org; any row where retire has access the survivor lacks = a gap to add

SELECT Parent.Label, Parent.IsOwnedByProfile, Field, PermissionsRead, PermissionsEdit

FROM FieldPermissions

WHERE Field IN ('Account.of_Attorneys__c','Account.Number_of_Attorneys__c')

ORDER BY Parent.Label, Field

How. Edit the retrieved permissionset-meta.xml (and any profile that shows a gap) to add the survivor fieldPermissions entry, deploy.

Validation. Re-run the FLS query; survivor access ≥ retire access for every parent. Rollback. Redeploy Step 0 baseline of the permission sets/profiles.

# Step 2 — Pre-migration data backup (PROD/FULLUAT only)

Why. This export is both an audit artifact and the rollback source for Step 3.

-- export to CSV, keep with timestamp; ~29,684 rows

SELECT Id, of_Attorneys__c, Number_of_Attorneys__c

FROM Account

WHERE of_Attorneys__c != null

Store as attorney_backup_PROD_YYYYMMDD.csv. Verify row count ≈ 29,684 (prod, 2026-06-19).

# Step 3 — Data migration: Number_of_Attorneys__c := of_Attorneys__c (PROD/FULLUAT only)

Scope (prod, 2026-06-19): 738,825 Accounts; 731 records change = 109 survivor-blank + 622 conflicts (RETIRE-wins). The other 28,953 already match; 204 survivor-only are untouched. *(SURVIVOR-wins variant → only the 109 blanks change.)*

Recommended method — Data Loader (no code, fully auditable):

- From the Step 2 export, compute the update set in a spreadsheet: rows where Number_of_Attorneys__c <> of_Attorneys__c (incl. blank survivor) → set new Number_of_Attorneys__c = of_Attorneys__c. Expect ~731 rows.

- Data Loader Update with Id, Number_of_Attorneys__c.

- Grain note: the set naturally includes both office and Firm (Ultimate Account) records, so the CPQ quote formula (Quote.Number_of_Attorneys__c → Account.Ultimate_Account__r.Number_of_Attorneys__c) is satisfied (Phase 1 §6b).

Coded alternative — Batch Apex (200 scope) if trigger cascades/limits are a concern; compare per-record and update only where different. Avoid a single anonymous-Apex pass over all 29,684 (sync heap risk).

Side-effects check. Updating attorney count does not fire the Account Update Industry Category before-save flow (it triggers only on Industry_Data_Provider__c / Industry_Category_Override__c / Industry_ALM__c changes). Other Account triggers will fire on 731 updates — small; run in a low-traffic window. Consider the org bypass (Application_Settings__c) only if needed.

Validation. Re-run the conflict query (Phase 1 method: pull both-populated set, compare client-side) → expect 0 differing, 0 survivor-blank-where-retire-populated. Rollback. Data Loader Update from attorney_backup_*.csv (Id, Number_of_Attorneys__c original values) restores prior survivor values exactly. Window: anytime (data is retained).

# Step 4 — Repoint the two formula fields → survivor (metadata)

Why/Order. Must run after Step 3 in PROD so output is unchanged. A formula referencing of_Attorneys__c also blocks deletion of the field, so this must precede Step 9.

Edits (token-for-token swap, thresholds unchanged):

- Account.Industry_Category__c: replace each of_Attorneys__c → Number_of_Attorneys__c (3 occurrences; ≥151/≥71/≥6/≤5 buckets).

- Account.ALM_Industry_Category_Code__c: replace each of_Attorneys__c → Number_of_Attorneys__c (≥151/≥71/≥6 buckets, incl. the ISBLANK(...) guard).

Validation (KJDEV, synthetic data since org is empty): create ~6 test Accounts spanning the thresholds (e.g. attorney counts 3, 6, 71, 151, 0/blank) with of_Attorneys__c = Number_of_Attorneys__c and Industry_ALM__c = "Law Firm"; snapshot Industry_Category__c + ALM_Industry_Category_Code__c before deploy, repoint, confirm identical after. In FULLUAT/PROD (post-migration), spot-check several of the former 622 conflicts → category unchanged. Rollback. Redeploy Step 0 baseline of the two formula fields.

# Step 5 — Swap the field on the two layouts (metadata)

Why. Both layouts show of_Attorneys__c (editable) and neither shows the survivor — swap so users keep an attorney field and stop writing to the retire field.

Edits: in Account-Firm Layout and Account-Office Layout - Data Team, change <field>of_Attorneys__c</field> → <field>Number_of_Attorneys__c</field> (same position/Edit behavior). Validation. Open each layout; survivor present where retire was; retire absent. Rollback. Redeploy Step 0 baseline of the two layouts.

# Step 6 — Re-run the Phase 1 audit (prove zero remaining references)

Before any deprecation, re-confirm of_Attorneys__c is referenced by nothing except its own definition:

- Tooling dependency graph by Id (RefMetadataComponentId = '00NPx00000ACARFMA5') → expect 0.

- Grep retrieved Account object + layouts + the two formulas → only the field's own definition remains.

- CPQ rules + templates re-scan in PROD (Phase 1 §6/§6b columns) → 0 (already clean).

Gate: do not proceed to Step 8/9 until this is clean.

# Step 7 — Redirect go-forward stewardship & downstream consumer (PROD config/people)

Why. of_Attorneys__c is human-maintained by the ALM/Law.com data team (Phase 1) and read by Data Cloud.

- ALM data team switches data entry to Number_of_Attorneys__c; any Data Loader/ETL job remapped to the survivor.

- Lead conversion: confirm in Setup → Object Manager → Lead → Map Lead Fields whether ALM_of_Attorneys__c maps to Account.of_Attorneys__c; if so, remap to Number_of_Attorneys__c.

- Data Cloud: if a data stream ingests of_Attorneys__c, remap the stream/DLO mapping to the survivor.

Rollback. Revert mapping/config; resume old field entry (only meaningful before Step 9).

# Step 8 — Deprecate of_Attorneys__c (metadata, non-destructive)

Why. Stop new writes and signal retirement while keeping data for a soak period (safety net before deletion).

- Remove from all layouts (done in Step 5).

- Relabel → ALM # of Attorneys (DEPRECATED — use Number of Attorneys); add inline help pointing to the survivor.

- Tighten FLS to read-only (remove Edit everywhere) so nothing writes it during the soak.

Soak: agree a window (e.g. 2–4 weeks) to confirm no process/report/user breaks. Rollback. Redeploy baseline label/FLS; re-add to layouts.

# Step 9 — DELETE of_Attorneys__c (destructive — separate explicit confirmation)

Preconditions: Step 6 clean, Step 8 soak elapsed with no issues, reports/lead-map manual checks done, stakeholder + data-team go-ahead.

How: destructive deploy (destructiveChangesPost.xml with CustomField = Account.of_Attorneys__c, empty package.xml), KJDEV → FULLUAT → PROD.

<!-- destructiveChangesPost.xml -->

<Package xmlns="http://soap.sforce.com/2006/04/metadata">

<types><members>Account.of_Attorneys__c</members><name>CustomField</name></types>

</Package>

Never run a destructive deploy without an explicit, separate "yes" for this exact step.

Rollback / recovery.

- ≤15 days: Setup → Object Manager → Account → Fields → *Deleted Fields* → Undelete (restores field + data). API name stays reserved during this window.

- After permanent erase: field must be recreated (API name was locked); restore values from attorney_backup_*.csv. Treat post-erase as effectively irreversible — hence the soak.

# Rollback master table

| Step | Rollback action | Window |
| --- | --- | --- |
| 1 FLS | Redeploy baseline permission sets/profiles | anytime |
| 3 Data migration | Data Loader update from attorney_backup_*.csv | anytime (pre-Step 9) |
| 4 Formulas | Redeploy baseline formula fields | anytime |
| 5 Layouts | Redeploy baseline layouts | anytime |
| 7 Stewardship/Data Cloud | Revert mappings, resume old entry | before Step 9 |
| 8 Deprecate | Redeploy baseline label/FLS, re-add to layouts | anytime |
| 9 Delete | Undelete (≤15 days) → else recreate + reload backup | 15 days, then hard |

# Residual manual checks (carry from Phase 1)

- Reports/dashboards (6,424): run the field's Setup "Where is this used?" in PROD (covers reports) — too many to grep; dependency graph already clean. Do before Step 9.

- Lead conversion map: Step 7.

# Open decisions for sign-off

- Conflict tie-break: confirm RETIRE-wins (default, behavior-neutral) vs SURVIVOR-wins. *(Needs ALM data-team OK — changes 622 values.)*

- Go-forward owner: ALM data team commits to maintaining Number_of_Attorneys__c.

- Soak length before deletion (suggest 2–4 weeks).

- Deprecate-only vs delete: OK to plan toward deletion, or stop at deprecation indefinitely?

On your approval of these, Phase 3 begins at Step 0 in KJDEV — diffs shown, nothing deployed without your go-ahead.